## WBS
Levi's CMS System SI | [5 empty] | Creater | Create Date |  | Updater | UpdateDate
[6 empty] | 汪 | 2019-11-06 |  | 汪 | 2019-11-06
Task - ID |  |  | Task Name | Resource | Reviewer | Plan |  |  | Actuality |  |  | Completion Rate | Deliverable | [6 empty] | 2019-10-19 | 2019-10-20 | 2019-10-21 | 2019-10-22 | 2019-10-23 | 2019-10-24 | 2019-10-25 | 2019-10-26 | 2019-10-27 | 2019-10-28 | 2019-10-29 | 2019-10-30 | 2019-10-31 | 2019-11-01 | 2019-11-02 | 2019-11-03 | 2019-11-04 | 2019-11-05 | 2019-11-06 | 2019-11-07 | 2019-11-08 | 2019-11-09 | 2019-11-10 | 2019-11-11 | 2019-11-12 | 2019-11-13 | 2019-11-14 | 2019-11-15 | 2019-11-16 | 2019-11-17 | 2019-11-18 | 2019-11-19 | 2019-11-20 | 2019-11-21 | 2019-11-22
[6 empty] | Start (YMD) | End (YMD) | Cost (human hour） | Start (YMD) | End (YMD) | Cost (human hour） |  |  | BCWS | BCWP | ACWP |  |  |  | 周四 | 周五 | 周六 | 周日 | 周一 | 周二 | 周三 | 周四 | 周五 | 周六 | 周日 | 周一 | 周二 | 周三 | 周四 | 周五 | 周六 | 周日 | 周一 | 周二 | 周三 | 周四 | 周五 | 周六 | 周日 | 周一 | 周二 | 周三 | 周四 | 周五 | 周六 | 周日 | 周一 | 周二 | 周三
0 |  |  | 项目全体管理 |  |  | 2019-11-11 | 2019-12-03 | [6 empty] | 0 | 0 | 0
0 | 1 |  | kickoff会议 | SA | 汪 | 2019-11-11 | 2019-11-11 | 0 |  |  |  |  | 暂不计算工时 | 0 | 0 | 0
0 | 2 |  | 项目管理用文档模板做成 | SA | 汪 | 2019-11-11 | 2019-11-11 | 8 | 2019-11-11 | 2019-11-11 | 8 | 100% |  | 8 | 8 | 8
0 | 3 |  | 进度管理 | SA | 汪 | 2019-11-11 | 2019-12-03 | 8 | [5 empty] | 8 | 0 | 0
0 | 4 |  | 会议记录整理 | SA | 汪 | [7 empty] | 暂无执行计划
0 | 5 |  | 变更管理 | SA | 汪 | [7 empty] | 暂无执行计划
0 | 6 |  | 全体管理 | SA | 汪 | [7 empty] | 暂无执行计划
0 | 7
1 |  |  | 设备选型POC |  |  | 2019-11-11 | 2019-11-15 | [6 empty] | 0 | 0 | 0
1 | 1 |  | LED设备 |  |  | 2019-11-11 | 2019-11-15 | [6 empty] | 0 | 0 | 0
1 | 1 | 1 | LED设备整体效果图编制 | LS CHN | Hennry | 2019-11-11 | 2019-11-15 | 0 | [5 empty] | 0 | 0 | 0
1 | 1 | 2 | LED设备配置说明文档编制 | LS CHN | Hennry | 2019-11-11 | 2019-11-15 | 0 | [5 empty] | 0 | 0 | 0
1 | 1 | 3 | LED播放盒(V8)机型选型 | SA | 汪 | 2019-11-11 | 2019-11-15 | 0 | [5 empty] | 0 | 0 | 0
1 | 1 | 4 | LED设备施工点位图编制 | LS CHN | Hennry | 2019-11-11 | 2019-11-15 | 0 | [5 empty] | 0 | 0 | 0
1 | 1 | 5 | LED设备施工图编制 | SA | 汪 | 2019-11-11 | 2019-11-15 | 0 | [5 empty] | 0 | 0 | 0
1 | 1 | 6
1 | 2 |  | LCD设备
1 | 2 | 1 | LCD设备整体效果图编制 | LS CHN | Hennry | 2019-11-11 | 2019-11-15 | 0 | [5 empty] | 0 | 0 | 0
1 | 2 | 2 | LCD设备选型 | SA | 汪 | 2019-11-11 | 2019-11-15 | 0 | [5 empty] | 0 | 0 | 0
1 | 2 | 3 | LCD设备配置说明文档编制 | LS CHN | Hennry | 2019-11-11 | 2019-11-15 | 0 | [5 empty] | 0 | 0 | 0
1 | 2 | 4 | LCD设备施工点位图编制 | LS CHN | Hennry | 2019-11-11 | 2019-11-15 | 0 | [5 empty] | 0 | 0 | 0
1 | 2 | 5 | LCD设备安装配件选型 | SA | 汪 | 2019-11-11 | 2019-11-15 | 0 | [5 empty] | 0 | 0 | 0
1 | 2 | 6 | LCD设备安装配件说明文档编制 | SA | 汪 | 2019-11-11 | 2019-11-15 | 0 | [5 empty] | 0 | 0 | 0
1 | 2 | 7 | LCD设备施工图编制 | SA | 汪 | 2019-11-11 | 2019-11-15 | 0 | [5 empty] | 0 | 0 | 0
1 | 2 | 8 | LCD设备采购规划 | LS CHN | Hennry | 2019-11-11 | 2019-11-15 | 0 | [5 empty] | 0 | 0 | 0
1 | 2 | 9
1 | 3 |  | 移动终端设备 | [9 empty] | 无需求
1 | 3 | 1 | 移动终端设备整体效果图编制
1 | 3 | 2 | 移动终端设备选型
1 | 3 | 3 | 移动终端设备配置说明文档编制
1 | 3 | 4 | 移动终端CMS软件功能测试
1 | 3 | 5 | 移动终端CMS软件下载安装测试
1 | 3 | 6
2 |  |  | 设备制造/采购 |  |  | 2019-11-18 | 2019-11-22 | [6 empty] | 0 | 0 | 0
2 | 1 |  | LED设备 |  |  | 2019-11-18 | 2019-11-22 | [6 empty] | 0 | 0 | 0
2 | 1 | 1 | LED播放盒(V8)采购下单 | DY | 张 | 2019-11-18 | 2019-11-22 | 0 | [5 empty] | 0 | 0 | 0
2 | 1 | 2 | LED播放盒(V8)制造 | ST | 季 | 2019-11-18 | 2019-11-22 | 0 | [5 empty] | 0 | 0 | 0
2 | 1 | 3 | LED播放盒(V8)出口审核
2 | 1 | 4
2 | 2 |  | LCD设备 |  |  | 2019-11-18 | 2019-11-22 | [6 empty] | 0 | 0 | 0
2 | 2 | 1 | LCD设备采购下单 | DY | 张 | 2019-11-18 | 2019-11-22 | 0 | [5 empty] | 0 | 0 | 0
2 | 2 | 2 | LCD设备制造 | ST | 季 | 2019-11-18 | 2019-11-22 | 0 | [5 empty] | 0 | 0 | 0
2 | 2 | 3 | LCD设备验收 | DY | 张 | 2019-11-18 | 2019-11-22 | 0 | [5 empty] | 0 | 0 | 0
2 | 2 | 4 | LCD设备出口审核
2 | 2 | 5
2 | 3 |  | 移动终端设备 | [9 empty] | 无需求
2 | 3 | 1 | 移动终端设备预装
2 | 3 | 2 | 移动终端设备验收
2 | 3 | 3
3 |  |  | 设备物流 |  |  | 2019-11-25 | 2019-11-27 | [6 empty] | 0 | 0 | 0
3 | 1 |  | LED设备 |  |  | 2019-11-25 | 2019-11-27 | [6 empty] | 0 | 0 | 0
3 | 1 | 1 | LED播放盒(V8)物流方式确认 | ST | 季 | 2019-11-25 | 2019-11-27 | 0 | [5 empty] | 0 | 0 | 0
3 | 1 | 2 | LED播放盒(V8)物流采购 | ST | 季 | 2019-11-25 | 2019-11-27 | 0 | [5 empty] | 0 | 0 | 0
3 | 1 | 3 | LED播放盒(V8)装箱 | ST | 季 | 2019-11-25 | 2019-11-27 | 0 | [5 empty] | 0 | 0 | 0
3 | 1 | 4 | LED播放盒(V8)中国出关
3 | 1 | 5 | LED播放盒(V8)运输 | ST | 季 | 2019-11-25 | 2019-11-27 | 0 | [5 empty] | 0 | 0 | 0
3 | 1 | 6 | LED播放盒(V8)入关
3 | 1 | 7 | LED播放盒(V8)仓库至门店配送 | ST | 季 | 2019-11-25 | 2019-11-27 | 0 | [5 empty] | 0 | 0 | 0
3 | 1 | 8 | LED播放盒(V8)检收 | ST | 季 | 2019-11-25 | 2019-11-27 | 0 | [5 empty] | 0 | 0 | 0
3 | 1 | 9
3 | 2 |  | LCD设备 |  |  | 2019-11-25 | 2019-11-27 | [6 empty] | 0 | 0 | 0
3 | 2 | 1 | LCD设备物流方式确认 | ST | 季 | 2019-11-25 | 2019-11-27 | 0 | [5 empty] | 0 | 0 | 0
3 | 2 | 2 | LCD设备物流采购 | ST | 季 | 2019-11-25 | 2019-11-27 | 0 | [5 empty] | 0 | 0 | 0
3 | 2 | 3 | LCD设备装箱 | ST | 季 | 2019-11-25 | 2019-11-27 | 0 | [5 empty] | 0 | 0 | 0
3 | 2 | 4 | LCD设备中国出关
3 | 2 | 5 | LCD设备运输 | ST | 季 | 2019-11-25 | 2019-11-27 | 0 | [5 empty] | 0 | 0 | 0
3 | 2 | 6 | LCD设备入关
3 | 2 | 7 | LCD设备仓库至门店配送 | ST | 季 | 2019-11-25 | 2019-11-27 | 0 | [5 empty] | 0 | 0 | 0
3 | 2 | 8 | LCD设备检收 | ST | 季 | 2019-11-25 | 2019-11-27 | 0 | [5 empty] | 0 | 0 | 0
3 | 2 | 9
4 |  |  | 设备安装
4 | 1 |  | LED设备 | [9 empty] | 无需求
4 | 1 | 1 | LED设备交付
4 | 1 | 2
4 | 2 |  | LCD设备 | [9 empty] | 无需求
4 | 2 | 1 | LCD设备交付
4 | 2 | 2
4 | 3 |  | 移动终端设备 | [9 empty] | 无需求
4 | 3 | 1 | 移动终端设备交付
4 | 3 | 2
5 |  |  | LCD系统导入 |  |  | 2019-11-25 | 2019-12-03 | [6 empty] | 0 | 0 | 0
5 | 1 |  | 导入准备 |  |  | 2019-11-25 | 2019-12-03 | [6 empty] | 0 | 0 | 0
5 | 1 | 1 | 路由器询价 | DY | 张 | 2019-11-25 | 2019-11-29 | 0 | [5 empty] | 0 | 0 | 0
5 | 1 | 2 | 路由器采购 | DY | 张 | 2019-11-25 | 2019-11-29 | 0 | [5 empty] | 0 | 0 | 0
5 | 1 | 3 | 路由器采购&配送 | DY | 张 | 2019-11-25 | 2019-11-29 | 0 | [5 empty] | 0 | 0 | 0
5 | 1 | 4 | 专用账号登记 | SA | 汪 | 2019-11-25 | 2019-11-29 | 2 | [5 empty] | 2 | 0 | 0
5 | 1 | 5 | 网络防火墙设置沟通（for CMS） | SA | 汪 | 2019-11-25 | 2019-11-29 | 2 | [5 empty] | 2 | 0 | 0
5 | 1 | 6 | 安装线路设计 | SA | 汪 | 2019-11-25 | 2019-11-29 | 2 | [5 empty] | 2 | 0 | 0
5 | 1 | 7 | 各楼层单屏内容编制 | ST | 季 | 2019-11-25 | 2019-12-03 | 0 | [5 empty] | 0 | 0 | 0
5 | 1 | 8 | 各楼层单屏内容审核 | LS | Hennry | 2019-11-25 | 2019-12-03 | 0 | [5 empty] | 0 | 0 | 0
5 | 1 | 9 | 各楼层拼接屏设备内容编制 | ST | 季 | 2019-11-25 | 2019-12-03 | 0 | [5 empty] | 0 | 0 | 0
5 | 1 | 10 | 各楼层拼接屏设备内容审核 | LS | Hennry | 2019-11-25 | 2019-12-03 | 0 | [5 empty] | 0 | 0 | 0
5 | 1 | 11
5 | 2 |  | 导入执行 |  |  | 2019-11-27 | 2019-11-29 | [6 empty] | 0 | 0 | 0
5 | 2 | 1 | 现场勘察 | SA IND | 汪 | 2019-11-27 | 2019-11-29 | 4 | [5 empty] | 4 | 0 | 0
5 | 2 | 2 | 导入计划编制 | SA | 汪 | 2019-11-27 | 2019-11-29 | 0 | [5 empty] | 0 | 0 | 0
5 | 2 | 3 | 设备检收确认 | SA IND | 汪 | 2019-11-27 | 2019-11-29 | 4 | [5 empty] | 4 | 0 | 0
5 | 2 | 4 | LCD设备CMS导入 | SA IND
5 | 2 | 5 | LED设备CMS导入 | SA IND | 汪 | 2019-11-27 | 2019-11-29 | 4 | [5 empty] | 4 | 0 | 0
5 | 1 | 6 | CMS&屏幕&盒子绑定确认 | SA IND | 汪 | 2019-11-27 | 2019-11-29 | 2 | [5 empty] | 2 | 0 | 0
5 | 2 | 7 | LED内容确认(音频/视频/图片) | SA IND | 汪 | 2019-11-27 | 2019-11-29 | 2 | [5 empty] | 2 | 0 | 0
5 | 2 | 8 | LCD内容确认(音频/视频/图片) | SA IND
5 | 2 | 9 | 移动终端内容确认(音频/视频/图片) | SA IND
5 | 2 | 10
6 |  |  | 项目测试 |  |  | 2019-12-01 | 2019-12-03 | [6 empty] | 0 | 0 | 0
6 | 1 |  | CMS内容推送测试 | ST | 季 | 2019-12-01 | 2019-12-03 | 0 | [5 empty] | 0 | 0 | 0
6 | 2 |  | 设备长时间运行测试 | ST | 季 | 2019-12-01 | 2019-12-03 | 0 | [5 empty] | 0 | 0 | 0
6 | 3
7 |  |  | 项目验收 |  |  | 2019-12-01 | 2019-12-03 | [6 empty] | 0 | 0 | 0
7 | 1 |  | 现场验收取证 | SA IND | 汪 | 2019-12-01 | 2019-12-03 | 0 | [5 empty] | 0 | 0 | 0
7 | 2 |  | 完工报告书编制 | SA IND | 汪 | 2019-12-01 | 2019-12-03 | 2 | [5 empty] | 2 | 0 | 0
7 | 3
[7 empty] | 计划完成日期 | 计划工时总计 |  | 实际完成日期 | 实际工时总计
[7 empty] | 2019-12-03 | 40 |  | 2019-11-11 | 8
[14 empty] | PV | EV | AC | BAC
[14 empty] | 40 | 8 | 8 | 40
[14 empty] | SV | CV | CPI | SPI | ETC | EAC
[14 empty] | -32 | 0 | 100% | 20% | 32 | #REF!
注：
１、BCWS=PV, BCWP=EV, ACWP=AC, BAC（Budget at Completion）,
ETC(Estimation to complete), EAC(Estimation at complete)
2、SV=EV-PV, CV=EV-AC
3、CPI=EV/AC, SPI=EV/PV
４、ETC=BAC-EV, EAC=AC+ETC
Formulas:
BCWS = IF([Create Date]="","",IF([Create Date]<=L2,[Cost (human hour）],IF([Creater]<=L2,NETWORKDAYS([Creater],L2,holiday!$C3:C10)/NETWORKDAYS([Creater],[Create Date],holiday!$C3:C10)*[Cost (human hour）],0)))
Note on R5: Budgeted Cost for Work Scheduled
Note on S5: Budgeted Cost for Work Performed
Note on T5: Actual Cost for Work Performed
Note on R121: Plan Value
Note on S121: Earned Value
Note on T121: Actual Cost
Note on U121: Budget at completion
Note on R125: Schedule Variance
Note on S125: Cost Variance
Note on T125: Cost Peformance Index
Note on U125: Schedule Performance Index
Note on V125: Estimation to ｃomplete
Note on W125: Estimation at complete

## 個人 (2) (hidden)
WBS For eMuSC地銀展開（関東つくば銀行） | [11 empty] | 作成者 | 作成日 | 更新者 | 更新日
[12 empty] | 劉 嵩斌 | 2007-02-28
Task - ID |  |  |  | Task名 | PC | i-mode | softbank | Ezweb | 担当 | PeerReview 担当 | Sub担当 | 予定 |  |  | 実績 |  |  | 進捗 | 成果物 (予定)
[6 empty] | (NTT DoCoMo) | (vodafone) | (au) |  |  |  | Start(YMD) | End(YMD) | 予定工数(人時間） | Start(YMD) | End(YMD) | 実績工数(人時間） |  |  | BCWS | BCWP | ACWP
0 |  |  |  | プロジェクト管理
0 | 1 |  |  | プロジェクト計画の作成 |  |  |  |  | 丁 |  |  | 2007-01-23 | 2007-02-09 | 20 | 2007-02-04 | 2007-02-09 | 20 | 100% | ISSC内部計画など | 20 | 20 | 20
0 | 2 |  |  | ピアーレビュー計画の作成 |  |  |  |  | 毛、楊、劉 |  |  | 2007-03-12 | 2007-03-16 | 20 |  |  | 40 | 8% | WBSなど | 20 | 1.6 | 40
0 | 3 |  |  | プロジェクト日常管理 |  |  |  |  | 丁、毛 |  |  | 2007-03-01 | 2007-05-31 | 484 | 2007-03-01 |  |  |  | 進捗報告・ISSC内部報告 | 484 | 0 | 0
0 | 4 |  |  | PQA・QAレビューおよび対応 |  |  |  |  | 丁、毛 |  |  | 2007-04-16 | 2007-05-31 | 16 | 2007-03-01 |  |  |  | ISSC内部報告 | 16 | 0 | 0
0 | 5 |  |  | 技術サポート（Traning）・開発レビュー・共通作業 |  |  |  |  | 劉 |  |  | 2007-03-12 | 2007-04-06 | 120 |  |  |  |  | なし | 120 | 0 | 0
|  |  |  | 開発 | 164 | 164 | 164 | 184
1 |  |  |  | 事前準備
1 | 1 |  |  | 開発環境の準備 |  |  |  |  | 劉 嵩斌 |  |  | 2007-03-05 | 2007-03-09 | 40 | 2007-03-05 |  | 16 | 40% |  | 40 | 16 | 16
1 | 2 |  |  | 開発方針・コーディングガイド理解 |  |  |  |  | 全員 |  |  | 2007-03-12 | 2007-03-19 | 80 |  |  |  |  | UTチェックリスト・ガイド | 80 | 0 | 0
1 | 3 |  |  | 基盤クラスの理解(Skill横展開) |  |  |  |  | 全員 |  |  | 2007-03-13 | 2007-03-19 | 80 | [5 empty] | 80 | 0 | 0
1 | 4 |  |  | 仕様理解 |  |  |  |  | 全員 |  |  | 2007-03-12 | 2007-04-09 | 30 | [5 empty] | 30 | 0 | 0
1 | 5 |  |  | 個別機能の調査・確認 |  |  |  |  | 全員 |  |  | 2007-03-12 | 2007-04-12 | 30 | [5 empty] | 30 | 0 | 0
1 | 6 |  |  | Q&Aやりとり |  |  |  |  | 全員 |  |  | 2007-03-12 | 2007-05-31 | 100 |  |  |  |  | Q&A票 | 100 | 0 | 0
2 |  |  |  | 実現（CD&UT&PeerReview) | 4 | 2 | 2 | 2
2 | 1 |  |  | ユーザ認証 | ● | ● | ● | ● | 李 鄂林 | 田 志軍 |  | 2007-03-14 | 2007-03-16 | 12 |  |  |  |  | ソース | 12 | 0 | 0
2 | 2 |  |  | 照会 | 4 | 5 | 5 | 5 | [10 empty] | 同上
2 | 2 | 1 |  | 残高照会 | ● | ● | ● | ● | 李 鄂林 | 田 志軍 |  | 2007-03-14 | 2007-03-16 | 12 | [5 empty] | 12 | 0 | 0
2 | 2 | 2 |  | 入出金明細照会（期間指定） | ● | ● | ● | ● | 李 鄂林 | 田 志軍 |  | 2007-03-19 | 2007-03-23 | 16
2 | 3 |  |  | 振込・振替 | 23 | 28 | 28 | 32 | [10 empty] | 同上
2 | 3 | 1 |  | お振替 | ● | ● | ● | ● | 田 志軍 | 徐 淳 |  | 2007-03-14 | 2007-03-23 | 32 | [5 empty] | 32 | 0 | 0
2 | 3 | 2 |  | お振込 | ● | ● | ● | ● | 田 志軍 | 徐 淳 |  | 2007-03-19 | 2007-03-30 | 72 | [5 empty] | 72 | 0 | 0
2 | 3 | 3 |  | 予約取消 | ● | ● | ● | ● | 张 文旭 | 田 志軍 |  | 2007-03-19 | 2007-03-23 | 20 | [5 empty] | 20 | 0 | 0
2 | 3 | 4 |  | 状況照会 | ● | ● | ● | ● | 张 文旭 | 田 志軍 |  | 2007-03-19 | 2007-03-23 | 20 | [5 empty] | 20 | 0 | 0
2 | 3 | 5 |  | 登録先削除 | ● | ● | ● | ● | 张 文旭 | 田 志軍 |  | 2007-03-26 | 2007-03-30 | 40 | [5 empty] | 40 | 0 | 0
2 | 5 |  |  | 口座確認
2 | 5 | 1 |  | 自行宛振込
2 | 5 | 2 |  | 他行宛振込
2 | 4 |  |  | 定期預金 | 33 | 38 | 38 | 38 | [10 empty] | 同上
2 | 4 | 1 |  | お預入れ | ● | ● | ● | ● | 徐 淳 | 田 志軍 |  | 2007-03-14 | 2007-03-23 | 64 | [5 empty] | 64 | 0 | 0
2 | 4 | 2 |  | お引出し | ● | ● | ● | ● | 徐 淳 | 田 志軍 |  | 2007-03-26 | 2007-03-30 | 40 | [5 empty] | 40 | 0 | 0
2 | 4 | 3 |  | 明細照会 | ● | ● | ● | ● | 叶 海波 | 徐 淳 |  | 2007-03-14 | 2007-03-16 | 24 | [5 empty] | 24 | 0 | 0
2 | 4 | 4 |  | 商品内容 | ● | ● | ● | ● | 叶 海波 | 徐 淳 |  | 2007-03-19 | 2007-03-23 | 20 | [5 empty] | 20 | 0 | 0
2 | 4 | 5 |  | 金利照会 | ● | ● | ● | ● | 叶 海波 | 徐 淳 |  | 2007-03-19 | 2007-03-23 | 20 | [5 empty] | 20 | 0 | 0
2 | 4 | 6 |  | 状況照会 | ● | ● | ● | ● | 叶 海波 | 徐 淳 |  | 2007-03-26 | 2007-03-30 | 40 | [5 empty] | 40 | 0 | 0
2 | 5 |  |  | その他 | 4 | 3 | 3 | 3 | [10 empty] | 同上
2 | 5 | 1 |  | ログオフ | ● | ● | ● | ● | 李 鄂林 | 田 志軍 |  | 2007-03-19 | 2007-03-23 | 5 | [5 empty] | 5 | 0 | 0
2 | 5 | 2 |  | セッションタイムアウト | ● | ● | ● | ● | 李 鄂林 | 田 志軍 |  | 2007-03-19 | 2007-03-23 | 5 | [5 empty] | 5 | 0 | 0
2 | 5 | 3 |  | システムエラー | ● | ● | ● | ● | 李 鄂林 | 田 志軍 |  | 2007-03-19 | 2007-03-23 | 6 | [5 empty] | 6 | 0 | 0
2 | 5 | 4 |  | ヘルプ | ● |  |  |  | 李 鄂林 | 田 志軍 |  | 2007-03-19 | 2007-03-23 | 8 | [5 empty] | 8 | 0 | 0
2 | 6 |  |  | ネットローン | 1
2 | 6 | 1 |  | ネットローンサービス | ●
2 | 7 |  |  | メンテナンス | 11 | 11 | 11 | 11 | [10 empty] | 同上
2 | 7 | 1 |  | ログオンパスワードの変更 | ● | ● | ● | ● | 李 鄂林 | 田 志軍 |  | 2007-03-26 | 2007-03-30 | 8 | [5 empty] | 8 | 0 | 0
2 | 7 | 3 |  | メールアドレスの登録・変更 | ● | ● | ● | ● | 李 鄂林 | 田 志軍 |  | 2007-03-26 | 2007-03-30 | 8 | [5 empty] | 8 | 0 | 0
2 | 7 | 4 |  | 振込限度額の照会・変更 | ● | ● | ● | ● | 李 鄂林 | 田 志軍 |  | 2007-03-26 | 2007-03-30 | 8 | [5 empty] | 8 | 0 | 0
2 | 8 |  |  | メッセージ | 3 | 5 | 5 | 5 | [10 empty] | 同上
2 | 8 | 1 |  | お知らせ | ● | ● | ● | ● | 李 鄂林 | 田 志軍 |  | 2007-03-26 | 2007-03-30 | 8 | [5 empty] | 8 | 0 | 0
2 | 8 | 2 |  | お取引内容 | ● | ● | ● | ● | 李 鄂林 | 田 志軍 |  | 2007-03-26 | 2007-03-30 | 8 | [5 empty] | 8 | 0 | 0
2 | 9 |  |  | オンライン収納 | [14 empty] | 同上
2 | 9 | 1 |  | 税金・各種料金の払込 | 30 | 37 | 37 | 47
2 | 9 | 1 | 1 | 国庫 | ● | ● | ● | ● | 潘 基徳 | 呉 文俊 |  | 2007-03-14 | 2007-03-16 | 24 | [5 empty] | 24 | 0 | 0
2 | 9 | 1 | 2 | 国税庁 | ● | ● | ● | ● | 潘 基徳 | 呉 文俊 |  | 2007-03-19 | 2007-03-23 | 20 | [5 empty] | 20 | 0 | 0
2 | 9 | 1 | 3 | 地公体 | ● | ● | ● | ● | 潘 基徳 | 呉 文俊 |  | 2007-03-19 | 2007-03-23 | 20 | [5 empty] | 20 | 0 | 0
2 | 9 | 1 | 4 | 民間 | ● | ● | ● | ● | 戚 灿灿 | 呉 文俊 |  | 2007-03-19 | 2007-03-23 | 40 | [5 empty] | 40 | 0 | 0
2 | 9 | 2 |  | 結果照会 | ● | ● | ● | ● | 潘 基徳 | 呉 文俊 |  | 2007-03-26 | 2007-03-30 | 40 | [5 empty] | 40 | 0 | 0
2 | 10 |  |  | 情報リンク | [14 empty] | 同上
2 | 10 | 1 |  | 税金・各種料金の払込 | 29 | 35 | 35 | 41
2 | 10 | 1 | 1 | 国庫 | ● | ● | ● | ● | 呉 文俊 | 潘 基徳 |  | 2007-03-14 | 2007-03-16 | 24 | [5 empty] | 24 | 0 | 0
2 | 10 | 1 | 2 | 国税庁 | ● | ● | ● | ● | 呉 文俊 | 潘 基徳 |  | 2007-03-19 | 2007-03-23 | 20 | [5 empty] | 20 | 0 | 0
2 | 10 | 1 | 3 | 地公体 | ● | ● | ● | ● | 呉 文俊 | 潘 基徳 |  | 2007-03-19 | 2007-03-23 | 20 | [5 empty] | 20 | 0 | 0
2 | 10 | 1 | 4 | 民間 | ● | ● | ● | ● | 呉 文俊 | 潘 基徳 |  | 2007-03-26 | 2007-03-30 | 40 | [5 empty] | 40 | 0 | 0
2 | 10 | 2 |  | 結果照会 | ● | ● | ● | ● | 戚 灿灿 | 呉 文俊 |  | 2007-03-26 | 2007-03-30 | 40 | [5 empty] | 40 | 0 | 0
2 | 11 |  |  | 受付業務 | [14 empty] | 同上
2 | 11 | 1 |  | 公共料金口座振替 | 23
2 | 11 | 1 | 1 | 電気 | ● |  |  |  | 李 明军 | 劉 嵩斌 |  | 2007-03-19 | 2007-03-23 | 6 | [5 empty] | 6 | 0 | 0
2 | 11 | 1 | 2 | NHK | ● |  |  |  | 李 明军 | 劉 嵩斌 |  | 2007-03-19 | 2007-03-23 | 6 | [5 empty] | 6 | 0 | 0
2 | 11 | 1 | 3 | 電話（NTT） | ● |  |  |  | 李 明军 | 劉 嵩斌 |  | 2007-03-19 | 2007-03-23 | 6 | [5 empty] | 6 | 0 | 0
2 | 11 | 1 | 4 | 携帯電話（Docomo） | ● |  |  |  | 李 明军 | 劉 嵩斌 |  | 2007-03-19 | 2007-03-23 | 6 | [5 empty] | 6 | 0 | 0
2 | 11 | 2 |  | 受付業務結果照会 | ● |  |  |  | 李 明军 | 劉 嵩斌 |  | 2007-03-19 | 2007-03-23 | 8 | [5 empty] | 8 | 0 | 0
2 | 11 | 3 |  | 住所変更受付 | ● |  |  |  | 李 明军 | 劉 嵩斌 |  | 2007-03-19 | 2007-03-23 | 8 | [5 empty] | 8 | 0 | 0
2 | 12 |  |  | IB業務個別修正 | [14 empty] | 同上
2 | 12 | 1 |  | 資金移動時のソフトウェアパスワード | ● |  |  |  | 劉 嵩斌 | 李 明军 |  | 2007-03-14 | 2007-03-16 | 8 | [5 empty] | 8 | 0 | 0
2 | 12 | 2 |  | その他 | ● |  |  |  | 李 明军 | 李 明军 |  | 2007-03-19 | 2007-03-23 | 40 | [5 empty] | 40 | 0 | 0
2 | 13 |  |  | 行内業務修正 | ● |  |  |  | 郭 秀山 | 劉 嵩斌 |  | 2007-03-14 | 2007-03-23 | 40 |  |  |  |  | 同上 | 40 | 0 | 0
2 | 14 |  |  | PKG障害取込み | ● |  |  |  | 郭 秀山 | 劉 嵩斌 |  | 2007-03-14 | 2007-04-30 | 24 |  |  |  |  | 同上 | #REF! | #REF! | #REF!
纏め作業
3 | 1 |  |  | コード整合と修正 |  |  |  |  | 全員 |  |  | 2007-03-16 | 2007-04-02 | 80 |  |  |  |  | 同上 | 80 | 0 | 0
3 | 2 |  |  | コード・レビュー実施 |  |  |  |  | 全員 |  |  | 2007-03-26 | 2007-04-03 | 40 |  |  |  |  | レビュー結果 | 40 | 0 | 0
3 | 3 |  |  | コード・レビュー結果対応 |  |  |  |  | 全員 |  |  | 2007-04-03 | 2007-04-06 | 40 |  |  |  |  | レビュー対応結果 | 40 | 0 | 0
3 | 4 |  |  | UTレビュー |  |  |  |  | 全員 |  |  | 2007-04-03 | 2007-04-06 | 160 |  |  |  |  | レビュー結果 | 160 | 0 | 0
3 | 5 |  |  | UTレビュー結果対応 |  |  |  |  | 全員 |  |  | 2007-04-03 | 2007-04-06 | 80 |  |  |  |  | レビュー対応結果 | 80 | 0 | 0
内部設計
4 | 1 |  |  | 共通コンポーネント一覧/内部レビュー（必要な場合） | [7 empty] | 2007-04-16 | 2007-04-30 | 10 |  |  |  |  | コンポーネント一覧 | 10 | 0 | 0
4 | 2 |  |  | 業務コンポーネント一覧/内部レビュー（必要な場合） | [7 empty] | 2007-04-16 | 2007-04-30 | 10 |  |  |  |  | コンポーネント一覧 | 10 | 0 | 0
4 | 3 |  |  | SQL一覧/内部レビュー（必要な場合） | [7 empty] | 2007-04-16 | 2007-04-30 | 16 |  |  |  |  | SQL一覧 | 16 | 0 | 0
[13 empty] | SUM: | 2392
[14 empty] | 14.95 | MM
[20 empty] | PV | EV | AC | SV
[20 empty] | #REF! | #REF! | #REF! | #REF!
Formulas:
BCWS = IF([作成日]="","",IF([作成日]<=TODAY(),[更新者],IF([作成者]<=TODAY(),DAYS360([作成者],TODAY())/DAYS360([作成者],[作成日])*[更新者],0)))
BCWP = IF([作成日]="","",IF([更新日]<=TODAY(),[更新者]*IF([進捗]<>"",[進捗],0),0))
BCWP = IF(#REF!="","",IF([更新日]<=TODAY(),#REF!*IF([進捗]<>"",[進捗],0),0))
ACWP = IF([作成日]="","",IF([更新日]<=TODAY(),IF([実績工数(人時間）]<>"",[実績工数(人時間）],[更新者]*IF([進捗]<>"",[進捗],0)),0))
ACWP = IF(#REF!="","",IF([更新日]<=TODAY(),IF([実績工数(人時間）]<>"",[実績工数(人時間）],#REF!*IF([進捗]<>"",[進捗],0)),0))
江越さんに確認する必要がある。
江越さんに確認する必要がある。

## holiday
No | Date | holiday | Transfer Date
1 | 2019-06-07 | 端午节(CN)
2 | 2019-07-15 | 海洋节(JP)
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20