## WBS for Sibuya
Levi's CMS System SI | [5 empty] | Creater | Create Date |  | Updater | UpdateDate
[6 empty] | 郭 | 2019-05-24 |  | 郭 | 2019-06-26
Task - ID |  |  | Task Name | Resource | Reviewer | Plan |  |  | Actuality |  |  | Completion Rate | Deliverable | [6 empty] | 2019-05-22 | 2019-05-23 | 2019-05-24 | 2019-05-25 | 2019-05-26 | 2019-05-27 | 2019-05-28 | 2019-05-29 | 2019-05-30 | 2019-05-31 | 2019-06-01 | 2019-06-02 | 2019-06-03 | 2019-06-04 | 2019-06-05 | 2019-06-06 | 2019-06-07 | 2019-06-08 | 2019-06-09 | 2019-06-10 | 2019-06-11 | 2019-06-12 | 2019-06-13 | 2019-06-14 | 2019-06-15 | 2019-06-16 | 2019-06-17 | 2019-06-18 | 2019-06-19 | 2019-06-20 | 2019-06-21 | 2019-06-22 | 2019-06-23 | 2019-06-24 | 2019-06-25
[6 empty] | Start (YMD) | End (YMD) | Cost (human hour） | Start (YMD) | End (YMD) | Cost (human hour） |  |  | BCWS | BCWP | ACWP |  |  |  | 周四 | 周五 | 周六 | 周日 | 周一 | 周二 | 周三 | 周四 | 周五 | 周六 | 周日 | 周一 | 周二 | 周三 | 周四 | 周五 | 周六 | 周日 | 周一 | 周二 | 周三 | 周四 | 周五 | 周六 | 周日 | 周一 | 周二 | 周三 | 周四 | 周五 | 周六 | 周日 | 周一 | 周二 | 周三
0 |  |  | 项目全体管理 |  |  | 2019-05-20 | 2019-07-31 | 56 | [5 empty] | 56 | 0 | 0
0 | 1 |  | kickoff会议 | 未苗 | 汪 | 2019-05-24 | 2019-05-24 | 0 | 2019-05-24 | 2019-05-24 | 0 | 100% | 暂不计算工时 | 0 | 0 | 0
0 | 2 |  | 项目管理用文档模板做成 | 未苗 | 汪 | 2019-05-20 | 2019-05-24 | 16 | 2019-05-20 |  | 8 | 100% |  | 16 | 16 | 8
0 | 3 |  | 进度管理 | 未苗 | 汪 | 2019-05-27 | 2019-07-19 | 40 | 2019-05-27 |  | 20 | 70% |  | 40 | 28 | 20
0 | 4 |  | 会议记录整理 | 未苗 | 陈 | 2019-05-27 | 2019-07-19 | 0 | 2019-05-27 |  |  |  | 暂无执行计划 | 0 | 0 | 0
0 | 5 |  | 变更管理 | 未苗 | 陈 | 2019-05-27 | 2019-07-19 | 0 | 2019-05-27 |  |  |  | 暂无执行计划 | 0 | 0 | 0
0 | 6 |  | 全体管理 | 未苗 | 汪 | 2019-05-27 | 2019-07-19 | 0 | 2019-05-27 |  |  |  | 暂无执行计划 | 0 | 0 | 0
0 | 7
1 |  |  | 设备选型POC |  |  | 2019-05-20 | 2019-05-31 | [6 empty] | 0 | 0 | 0
1 | 1 |  | LED设备 |  |  | 2019-05-27 | 2019-05-31 | [6 empty] | 0 | 0 | 0
1 | 1 | 1 | LED设备整体效果图编制 | 总包 | 张 | [6 empty] | 100% | \东京店\01 客户报价\前期方案\策划案效果图-Catr Sytreet 3Ds 1804.pdf
1 | 1 | 2 | LED设备配置说明文档编制 | LS JP | 荆 | [6 empty] | 100%
1 | 1 | 3 | LED播放盒(V8)机型选型 | 数拓 | 季 |  |  |  | 2019-06-10 | 2019-06-11 |  | 100% | \东京店\05 系统集成\LCD信息\ SHOWTOP3288(日本語版).doc SHOWTOP3288.doc | bar: 2019-06-10 to 2019-06-11
1 | 1 | 4 | LED设备施工点位图编制 | 总包 | 张 |  |  |  | 2019-06-07 | 2019-06-07 |  | 100% | \东京店\05 系统集成\LCD信息\ 室内拼接屏设置施工图-LS Cat Street 20190410 clean dwg v2.pdf(old) ★最新図面（平面図、立面図）0527.pdf Levis Harajuku LCD&LED Map.xlsx
1 | 1 | 5 | LED设备施工图编制 | LS JP | 荆 | [6 empty] | 100%
1 | 1 | 6
1 | 2 |  | 拼接屏设备 |  |  | 2019-05-27 | 2019-05-31 | [6 empty] | 0 | 0 | 0
1 | 2 | 1 | 拼接屏设备整体效果图编制 | 总包 | 张 | [6 empty] | 100% | \东京店\01 客户报价\前期方案\策划案效果图-Catr Sytreet 3Ds 1804.pdf
1 | 2 | 2 | 拼接屏设备选型 | 总包 | 张 | [6 empty] | 100% | \东京店\05 系统集成\LCD信息\HLN490PB(LG49寸3.5mm-500).doc
1 | 2 | 3 | 拼接屏设备配置说明文档编制 | LCD供应商 | 季 | [6 empty] | 100% | \东京店\05 系统集成\LCD信息\HLN490PB(LG49寸3.5mm-500).doc
1 | 2 | 4 | 拼接屏设备施工点位图编制 | 总包 | 张 |  |  |  | 2019-06-07 | 2019-06-07 |  | 100% | \东京店\05 系统集成\LCD信息\ 室内拼接屏设置施工图-LS Cat Street 20190410 clean dwg v2.pdf(old) ★最新図面（平面図、立面図）0527.pdf Levis Harajuku LCD&LED Map.xlsx
1 | 2 | 5 | 拼接屏设备安装配件选型 | LCD供应商 | 张 |  |  |  | 2019-06-17 | 2019-06-17 |  | 100% | \东京店\05 系统集成\配件信息 \东京店\05 系统集成\LCD信息\室内拼接屏1X1-49寸.dwg | bar: 2019-06-17
1 | 2 | 6 | 拼接屏设备安装配件说明文档编制 | LCD供应商 | 季 | [6 empty] | 100% | \东京店\05 系统集成\LCD信息\拼接安装调试文档.doc
1 | 2 | 7 | 拼接屏设备施工图编制 | LCD供应商 | 季 |  |  |  | 2019-05-30 | 2019-06-17 |  | 100% | \东京店\05 系统集成\LCD信息\室内拼接屏3X2-49寸.jpg \东京店\05 系统集成\LCD信息\室内拼接屏2X2-49寸.jpg \东京店\05 系统集成\LCD信息\室内拼接屏1X1-49寸.dwg | bar: 2019-05-30; 2019-06-02 to 2019-06-06; 2019-06-09 to 2019-06-13; 2019-06-16 to 2019-06-17
1 | 2 | 8 | 拼接屏设备采购规划 | 数拓 | 季 | [6 empty] | 100%
1 | 2 | 9
1 | 3 |  | 移动终端设备 |  |  | 2019-05-27 | 2019-05-31 | [6 empty] | 0 | 0 | 0
1 | 3 | 1 | 移动终端设备整体效果图编制 | LS CN | 张 | [6 empty] | 100% | \东京店\01 客户报价\前期方案\策划案效果图-Catr Sytreet 3Ds 1804.pdf
1 | 3 | 2 | 移动终端设备选型 | LS USA | 季 |  |  |  | 2019-06-14 | 2019-06-14 |  | 100%
1 | 3 | 3 | 移动终端设备配置说明文档编制 | LS USA | 季 |  |  |  | 2019-06-14 | 2019-06-14 |  | 100%
1 | 3 | 4 | 移动终端CMS软件功能测试 | 数拓 | 季 |  |  |  | 2019-06-15 | 2019-06-16 |  | 100% | bar: 2019-06-16
1 | 3 | 5 | 移动终端CMS软件下载安装测试 | 数拓 | 季 |  |  |  | 2019-06-15 | 2019-06-16 |  | 100% | bar: 2019-06-16
1 | 3 | 6
2 |  |  | 设备制造/采购 |  |  | 2019-05-27 | 2019-06-07 | [6 empty] | 0 | 0 | 0
2 | 1 |  | LED设备 |  |  | - | - | [6 empty] | 0 | 0 | 0
2 | 1 | 1 | LED设备采购确认 | LS JP | 荆 | [6 empty] | 100%
2 | 1 | 2 | LED播放盒(V8)制造 | 数拓 | 季 | [6 empty] | 100%
2 | 1 | 3 | LED播放盒(V8)出口审核 | 数拓 | 季 | [6 empty] | 100%
2 | 1 | 4
2 | 2 |  | 拼接屏设备 |  |  | 2019-05-27 | 2019-05-31 | [6 empty] | 0 | 0 | 0
2 | 2 | 1 | 拼接屏设备采购下单 | 数拓 | 季 | [6 empty] | 100%
2 | 2 | 2 | 拼接屏设备制造 | LED供应商 | 季 | [6 empty] | 100%
2 | 2 | 3 | 拼接屏设备验收 | 数拓 | 季 | [6 empty] | 100%
2 | 2 | 4 | 拼接屏设备出口审核 | 数拓 | 季 | 2019-05-28 | 2019-06-04 | 8 | 2019-05-28 | 2019-06-04 | 8 | 100% | \东京店\05 系统集成\LCD信息\ DL-2019051461C 数拓 显示屏 PSE J55032 证书.pdf DL-2019051461E 数拓 显示屏 PSE J55032 报告.pdf DL-2019051462C 数拓 显示屏 PSE J60950 证书.pdf DL-2019051462S 数拓 显示屏 PSE J60950 报告.pdf | 8 | 8 | 8 | bar: 2019-05-28 to 2019-05-30; 2019-06-02 to 2019-06-04
2 | 2 | 5
2 | 3 |  | 移动终端设备 |  |  | 2019-05-27 | 2019-06-07 | [6 empty] | 0 | 0 | 0
2 | 3 | 1 | 移动终端设备预装 | 数拓 | 季
2 | 3 | 2 | 移动终端设备验收 | 总包 | 张
2 | 3 | 3
3 |  |  | 设备物流 |  |  | 2019-05-27 | 2019-06-14 | [6 empty] | 0 | 0 | 0
3 | 1 |  | LED设备 |  |  | - | - | [6 empty] | 0 | 0 | 0
3 | 1 | 1 | LED设备仓库至门店配送 | LS JP | 荆
3 | 1 | 2
3 | 2 |  | 拼接屏设备 |  |  | 2019-05-27 | 2019-06-14 | [6 empty] | 0 | 0 | 0
3 | 2 | 1 | 拼接屏设备物流方式确认 | 总包 | 张 | [6 empty] | 100%
3 | 2 | 2 | 拼接屏设备物流采购 | 总包 | 张 | [6 empty] | 100%
3 | 2 | 3 | 拼接屏设备装箱 | 总包 | 张 | [6 empty] | 100%
3 | 2 | 4 | 拼接屏设备中国出关 | 总包 | 张 | [6 empty] | 100%
3 | 2 | 5 | 拼接屏设备运输 | 总包 | 张 | [6 empty] | 100%
3 | 2 | 6 | 拼接屏设备日本入关 | 总包 | 张 | [6 empty] | 100%
3 | 2 | 7 | 拼接屏设备仓库至门店配送 | 总包 | 张
3 | 2 | 8 | 拼接屏设备检收 | 总包 | 张
3 | 2 | 9
4 |  |  | 设备安装 |  |  | 2019-06-24 | 2019-06-28 | [6 empty] | 0 | 0 | 0
4 | 1 |  | LED设备 |  |  | 2019-06-24 | 2019-06-28 | [6 empty] | 0 | 0 | 0
4 | 1 | 1 | LED设备交付 | LS JP | 荆
4 | 1 | 2
4 | 2 |  | 拼接屏设备 |  |  | 2019-06-24 | 2019-06-28 | [6 empty] | 0 | 0 | 0
4 | 2 | 1 | 拼接屏设备交付 | LS JP | 荆
4 | 2 | 2
4 | 3 |  | 移动终端设备 |  |  | 2019-06-24 | 2019-06-28 | [6 empty] | 0 | 0 | 0
4 | 3 | 1 | 移动终端设备交付 | LS JP | 荆
4 | 3 | 2
5 |  |  | CMS系统导入 |  |  | 2019-06-03 | 2019-06-28 | 80 | [5 empty] | 80 | 0 | 0
5 | 1 |  | 导入准备 |  |  | 2019-06-03 | 2019-06-21 | 48 | [5 empty] | 48 | 0 | 0
5 | 1 | 1 | L2交换机询价 | 未苗JP | 荆 | 2019-05-27 | 2019-05-31 | 4 | 2019-06-12 | 2019-06-12 | 4 | 100% |  | 4 | 4 | 4 | bar: 2019-06-12
5 | 1 | 2 | L2交换机采购 | 未苗JP | 荆 | 2019-05-27 | 2019-05-31 | 4 | [5 empty] | 4 | 0 | 0
5 | 1 | 3 | L2交换机采购&配送 | 未苗JP | 荆
5 | 1 | 4 | JP-TKY-Sibuya专用账号登记 | 未苗JP | 荆 | 2019-05-27 | 2019-05-31 | 4 | 2019-06-06 |  | 4 | 50% | \东京店\05 系统集成\账号信息\Levi's CMS system accounts and equipments List(JP-TKY).xlsx | 4 | 2 | 4
5 | 1 | 5 | 上海网络防火墙设置沟通（for CMS） | 未苗 | 汪 | 2019-05-27 | 2019-05-28 | 4 | 2019-06-04 |  | 8 | 50% |  | 4 | 2 | 8
5 | 1 | 6 | 日本网络防火墙设置沟通（for IPad） | 未苗JP | 荆 | 2019-06-10 | 2019-06-14 | 8 | [5 empty] | 8 | 0 | 0
5 | 1 | 6 | 日本安装线路设计 | 未苗JP | 荆 | 2019-06-10 | 2019-06-14 | 24 | [5 empty] | 24 | 0 | 0
5 | 1 | 7 | LED设备内容编制 | 数拓 | 季
5 | 1 | 8 | LED设备内容审核 | LS CN | 张
5 | 1 | 9 | 各楼层拼接屏设备内容编制 | 数拓 | 陈
5 | 1 | 10 | 各楼层拼接屏设备内容审核 | LS CN | 张
5 | 1 | 11
5 | 2 |  | 导入执行 |  |  | 2019-07-01 | 2019-07-05 | 32 | [5 empty] | 32 | 0 | 0
5 | 2 | 1 | 日本东京涉谷现场勘察 | 未苗JP | 荆 | 2019-07-01 | 2019-07-01 | 8 | [5 empty] | 8 | 0 | 0
5 | 2 | 2 | 导入计划编制 | 未苗JP | 荆 | 2019-07-02 | 2019-07-02 | 4 | [5 empty] | 4 | 0 | 0
5 | 2 | 3 | 设备检收确认 | 未苗JP | 荆 | 2019-07-03 | 2019-07-03 | 4 | [5 empty] | 4 | 0 | 0
5 | 2 | 4 | LED设备CMS导入 | 未苗JP | 荆 | 2019-07-02 | 2019-07-05 | 2 | [5 empty] | 2 | 0 | 0
5 | 2 | 5 | 拼接屏设备CMS导入 | 未苗JP | 荆 | 2019-07-02 | 2019-07-05 | 6 | [6 empty] | 0 | 0
5 | 1 | 6 | CMS&屏幕&盒子绑定确认 | 未苗JP | 荆 | 2019-06-03 | 2019-06-14 | 4 | [5 empty] | 4 | 0 | 0
5 | 2 | 7 | LED内容确认(音频/视频/图片) | 未苗JP | 荆 | 2019-07-02 | 2019-07-05 | 1 | [5 empty] | 1 | 0 | 0
5 | 2 | 8 | 拼接屏内容确认(音频/视频/图片) | 未苗JP | 荆 | 2019-07-02 | 2019-07-05 | 2 | [5 empty] | 2 | 0 | 0
5 | 2 | 9 | 移动终端内容确认(音频/视频/图片) | 未苗JP | 荆 | 2019-07-02 | 2019-07-05 | 1 | [5 empty] | 1 | 0 | 0
5 | 2 | 10
6 |  |  | 项目测试 |  |  | 2019-07-01 | 2019-07-12 | [6 empty] | 0 | 0 | 0
6 | 1 |  | CMS内容推送测试 | 数拓 | 季 | 2019-07-01 | 2019-07-12 | [6 empty] | 0 | 0 | 0
6 | 2 |  | 设备长时间运行测试 | 数拓 | 季 | 2019-07-08 | 2019-07-12 | [6 empty] | 0 | 0 | 0
6 | 3
7 |  |  | 项目验收 |  |  | 2019-07-01 | 2019-07-15 | [6 empty] | 0 | 0 | 0
7 | 1 |  | 现场验收取证 | 未苗JP | 汪 | 2019-07-01 | 2019-07-12 | [6 empty] | 0 | 0 | 0
7 | 2 |  | 完工报告书编制 | 未苗 | 汪 | 2019-07-12 | 2019-07-15 | [6 empty] | 0 | 0 | 0
7 | 3
[7 empty] | 计划完成日期 | 计划工时总计 |  | 实际完成日期 | 实际工时总计
[7 empty] | 2019-07-31 | 360 |  | 2019-06-17 | 52
[14 empty] | PV | EV | AC | BAC
[14 empty] | 354 | 60 | 52 | 360
[14 empty] | SV | CV | CPI | SPI | ETC | EAC
[14 empty] | -294 | 8 | 115.4% | 16.95% | 300 | #REF!
注：
１、BCWS=PV, BCWP=EV, ACWP=AC, BAC（Budget at Completion）,
ETC(Estimation to complete), EAC(Estimation at complete)
2、SV=EV-PV, CV=EV-AC
3、CPI=EV/AC, SPI=EV/PV
４、ETC=BAC-EV, EAC=AC+ETC
Formulas:
BCWS = IF([Create Date]="","",IF([Create Date]<=L2,[Cost (human hour）],IF([Creater]<=L2,NETWORKDAYS([Creater],L2,holiday!$C3:C10)/NETWORKDAYS([Creater],[Create Date],holiday!$C3:C10)*[Cost (human hour）],0)))
Note on R5: Budgeted Cost for Work Scheduled
Note on S5: Budgeted Cost for Work Performed
Note on T5: Actual Cost for Work Performed
Note on R115: Plan Value
Note on S115: Earned Value
Note on T115: Actual Cost
Note on U115: Budget at completion
Note on R119: Schedule Variance
Note on S119: Cost Variance
Note on T119: Cost Peformance Index
Note on U119: Schedule Performance Index
Note on V119: Estimation to ｃomplete
Note on W119: Estimation at complete

## 個人 (2) (hidden)
WBS For eMuSC地銀展開（関東つくば銀行） | [11 empty] | 作成者 | 作成日 | 更新者 | 更新日
[12 empty] | 劉 嵩斌 | 2007-02-28
Task - ID |  |  |  | Task名 | PC | i-mode | softbank | Ezweb | 担当 | PeerReview 担当 | Sub担当 | 予定 |  |  | 実績 |  |  | 進捗 | 成果物 (予定)
[6 empty] | (NTT DoCoMo) | (vodafone) | (au) |  |  |  | Start(YMD) | End(YMD) | 予定工数(人時間） | Start(YMD) | End(YMD) | 実績工数(人時間） |  |  | BCWS | BCWP | ACWP
0 |  |  |  | プロジェクト管理
0 | 1 |  |  | プロジェクト計画の作成 |  |  |  |  | 丁 |  |  | 2007-01-23 | 2007-02-09 | 20 | 2007-02-04 | 2007-02-09 | 20 | 100% | ISSC内部計画など | 20 | 20 | 20
0 | 2 |  |  | ピアーレビュー計画の作成 |  |  |  |  | 毛、楊、劉 |  |  | 2007-03-12 | 2007-03-16 | 20 |  |  | 40 | 8% | WBSなど | 20 | 1.6 | 40
0 | 3 |  |  | プロジェクト日常管理 |  |  |  |  | 丁、毛 |  |  | 2007-03-01 | 2007-05-31 | 484 | 2007-03-01 |  |  |  | 進捗報告・ISSC内部報告 | 484 | 0 | 0
0 | 4 |  |  | PQA・QAレビューおよび対応 |  |  |  |  | 丁、毛 |  |  | 2007-04-16 | 2007-05-31 | 16 | 2007-03-01 |  |  |  | ISSC内部報告 | 16 | 0 | 0
0 | 5 |  |  | 技術サポート（Traning）・開発レビュー・共通作業 |  |  |  |  | 劉 |  |  | 2007-03-12 | 2007-04-06 | 120 |  |  |  |  | なし | 120 | 0 | 0
|  |  |  | 開発 | 164 | 164 | 164 | 184
1 |  |  |  | 事前準備
1 | 1 |  |  | 開発環境の準備 |  |  |  |  | 劉 嵩斌 |  |  | 2007-03-05 | 2007-03-09 | 40 | 2007-03-05 |  | 16 | 40% |  | 40 | 16 | 16
1 | 2 |  |  | 開発方針・コーディングガイド理解 |  |  |  |  | 全員 |  |  | 2007-03-12 | 2007-03-19 | 80 |  |  |  |  | UTチェックリスト・ガイド | 80 | 0 | 0
1 | 3 |  |  | 基盤クラスの理解(Skill横展開) |  |  |  |  | 全員 |  |  | 2007-03-13 | 2007-03-19 | 80 | [5 empty] | 80 | 0 | 0
1 | 4 |  |  | 仕様理解 |  |  |  |  | 全員 |  |  | 2007-03-12 | 2007-04-09 | 30 | [5 empty] | 30 | 0 | 0
1 | 5 |  |  | 個別機能の調査・確認 |  |  |  |  | 全員 |  |  | 2007-03-12 | 2007-04-12 | 30 | [5 empty] | 30 | 0 | 0
1 | 6 |  |  | Q&Aやりとり |  |  |  |  | 全員 |  |  | 2007-03-12 | 2007-05-31 | 100 |  |  |  |  | Q&A票 | 100 | 0 | 0
2 |  |  |  | 実現（CD&UT&PeerReview) | 4 | 2 | 2 | 2
2 | 1 |  |  | ユーザ認証 | ● | ● | ● | ● | 李 鄂林 | 田 志軍 |  | 2007-03-14 | 2007-03-16 | 12 |  |  |  |  | ソース | 12 | 0 | 0
2 | 2 |  |  | 照会 | 4 | 5 | 5 | 5 | [10 empty] | 同上
2 | 2 | 1 |  | 残高照会 | ● | ● | ● | ● | 李 鄂林 | 田 志軍 |  | 2007-03-14 | 2007-03-16 | 12 | [5 empty] | 12 | 0 | 0
2 | 2 | 2 |  | 入出金明細照会（期間指定） | ● | ● | ● | ● | 李 鄂林 | 田 志軍 |  | 2007-03-19 | 2007-03-23 | 16
2 | 3 |  |  | 振込・振替 | 23 | 28 | 28 | 32 | [10 empty] | 同上
2 | 3 | 1 |  | お振替 | ● | ● | ● | ● | 田 志軍 | 徐 淳 |  | 2007-03-14 | 2007-03-23 | 32 | [5 empty] | 32 | 0 | 0
2 | 3 | 2 |  | お振込 | ● | ● | ● | ● | 田 志軍 | 徐 淳 |  | 2007-03-19 | 2007-03-30 | 72 | [5 empty] | 72 | 0 | 0
2 | 3 | 3 |  | 予約取消 | ● | ● | ● | ● | 张 文旭 | 田 志軍 |  | 2007-03-19 | 2007-03-23 | 20 | [5 empty] | 20 | 0 | 0
2 | 3 | 4 |  | 状況照会 | ● | ● | ● | ● | 张 文旭 | 田 志軍 |  | 2007-03-19 | 2007-03-23 | 20 | [5 empty] | 20 | 0 | 0
2 | 3 | 5 |  | 登録先削除 | ● | ● | ● | ● | 张 文旭 | 田 志軍 |  | 2007-03-26 | 2007-03-30 | 40 | [5 empty] | 40 | 0 | 0
2 | 5 |  |  | 口座確認
2 | 5 | 1 |  | 自行宛振込
2 | 5 | 2 |  | 他行宛振込
2 | 4 |  |  | 定期預金 | 33 | 38 | 38 | 38 | [10 empty] | 同上
2 | 4 | 1 |  | お預入れ | ● | ● | ● | ● | 徐 淳 | 田 志軍 |  | 2007-03-14 | 2007-03-23 | 64 | [5 empty] | 64 | 0 | 0
2 | 4 | 2 |  | お引出し | ● | ● | ● | ● | 徐 淳 | 田 志軍 |  | 2007-03-26 | 2007-03-30 | 40 | [5 empty] | 40 | 0 | 0
2 | 4 | 3 |  | 明細照会 | ● | ● | ● | ● | 叶 海波 | 徐 淳 |  | 2007-03-14 | 2007-03-16 | 24 | [5 empty] | 24 | 0 | 0
2 | 4 | 4 |  | 商品内容 | ● | ● | ● | ● | 叶 海波 | 徐 淳 |  | 2007-03-19 | 2007-03-23 | 20 | [5 empty] | 20 | 0 | 0
2 | 4 | 5 |  | 金利照会 | ● | ● | ● | ● | 叶 海波 | 徐 淳 |  | 2007-03-19 | 2007-03-23 | 20 | [5 empty] | 20 | 0 | 0
2 | 4 | 6 |  | 状況照会 | ● | ● | ● | ● | 叶 海波 | 徐 淳 |  | 2007-03-26 | 2007-03-30 | 40 | [5 empty] | 40 | 0 | 0
2 | 5 |  |  | その他 | 4 | 3 | 3 | 3 | [10 empty] | 同上
2 | 5 | 1 |  | ログオフ | ● | ● | ● | ● | 李 鄂林 | 田 志軍 |  | 2007-03-19 | 2007-03-23 | 5 | [5 empty] | 5 | 0 | 0
2 | 5 | 2 |  | セッションタイムアウト | ● | ● | ● | ● | 李 鄂林 | 田 志軍 |  | 2007-03-19 | 2007-03-23 | 5 | [5 empty] | 5 | 0 | 0
2 | 5 | 3 |  | システムエラー | ● | ● | ● | ● | 李 鄂林 | 田 志軍 |  | 2007-03-19 | 2007-03-23 | 6 | [5 empty] | 6 | 0 | 0
2 | 5 | 4 |  | ヘルプ | ● |  |  |  | 李 鄂林 | 田 志軍 |  | 2007-03-19 | 2007-03-23 | 8 | [5 empty] | 8 | 0 | 0
2 | 6 |  |  | ネットローン | 1
2 | 6 | 1 |  | ネットローンサービス | ●
2 | 7 |  |  | メンテナンス | 11 | 11 | 11 | 11 | [10 empty] | 同上
2 | 7 | 1 |  | ログオンパスワードの変更 | ● | ● | ● | ● | 李 鄂林 | 田 志軍 |  | 2007-03-26 | 2007-03-30 | 8 | [5 empty] | 8 | 0 | 0
2 | 7 | 3 |  | メールアドレスの登録・変更 | ● | ● | ● | ● | 李 鄂林 | 田 志軍 |  | 2007-03-26 | 2007-03-30 | 8 | [5 empty] | 8 | 0 | 0
2 | 7 | 4 |  | 振込限度額の照会・変更 | ● | ● | ● | ● | 李 鄂林 | 田 志軍 |  | 2007-03-26 | 2007-03-30 | 8 | [5 empty] | 8 | 0 | 0
2 | 8 |  |  | メッセージ | 3 | 5 | 5 | 5 | [10 empty] | 同上
2 | 8 | 1 |  | お知らせ | ● | ● | ● | ● | 李 鄂林 | 田 志軍 |  | 2007-03-26 | 2007-03-30 | 8 | [5 empty] | 8 | 0 | 0
2 | 8 | 2 |  | お取引内容 | ● | ● | ● | ● | 李 鄂林 | 田 志軍 |  | 2007-03-26 | 2007-03-30 | 8 | [5 empty] | 8 | 0 | 0
2 | 9 |  |  | オンライン収納 | [14 empty] | 同上
2 | 9 | 1 |  | 税金・各種料金の払込 | 30 | 37 | 37 | 47
2 | 9 | 1 | 1 | 国庫 | ● | ● | ● | ● | 潘 基徳 | 呉 文俊 |  | 2007-03-14 | 2007-03-16 | 24 | [5 empty] | 24 | 0 | 0
2 | 9 | 1 | 2 | 国税庁 | ● | ● | ● | ● | 潘 基徳 | 呉 文俊 |  | 2007-03-19 | 2007-03-23 | 20 | [5 empty] | 20 | 0 | 0
2 | 9 | 1 | 3 | 地公体 | ● | ● | ● | ● | 潘 基徳 | 呉 文俊 |  | 2007-03-19 | 2007-03-23 | 20 | [5 empty] | 20 | 0 | 0
2 | 9 | 1 | 4 | 民間 | ● | ● | ● | ● | 戚 灿灿 | 呉 文俊 |  | 2007-03-19 | 2007-03-23 | 40 | [5 empty] | 40 | 0 | 0
2 | 9 | 2 |  | 結果照会 | ● | ● | ● | ● | 潘 基徳 | 呉 文俊 |  | 2007-03-26 | 2007-03-30 | 40 | [5 empty] | 40 | 0 | 0
2 | 10 |  |  | 情報リンク | [14 empty] | 同上
2 | 10 | 1 |  | 税金・各種料金の払込 | 29 | 35 | 35 | 41
2 | 10 | 1 | 1 | 国庫 | ● | ● | ● | ● | 呉 文俊 | 潘 基徳 |  | 2007-03-14 | 2007-03-16 | 24 | [5 empty] | 24 | 0 | 0
2 | 10 | 1 | 2 | 国税庁 | ● | ● | ● | ● | 呉 文俊 | 潘 基徳 |  | 2007-03-19 | 2007-03-23 | 20 | [5 empty] | 20 | 0 | 0
2 | 10 | 1 | 3 | 地公体 | ● | ● | ● | ● | 呉 文俊 | 潘 基徳 |  | 2007-03-19 | 2007-03-23 | 20 | [5 empty] | 20 | 0 | 0
2 | 10 | 1 | 4 | 民間 | ● | ● | ● | ● | 呉 文俊 | 潘 基徳 |  | 2007-03-26 | 2007-03-30 | 40 | [5 empty] | 40 | 0 | 0
2 | 10 | 2 |  | 結果照会 | ● | ● | ● | ● | 戚 灿灿 | 呉 文俊 |  | 2007-03-26 | 2007-03-30 | 40 | [5 empty] | 40 | 0 | 0
2 | 11 |  |  | 受付業務 | [14 empty] | 同上
2 | 11 | 1 |  | 公共料金口座振替 | 23
2 | 11 | 1 | 1 | 電気 | ● |  |  |  | 李 明军 | 劉 嵩斌 |  | 2007-03-19 | 2007-03-23 | 6 | [5 empty] | 6 | 0 | 0
2 | 11 | 1 | 2 | NHK | ● |  |  |  | 李 明军 | 劉 嵩斌 |  | 2007-03-19 | 2007-03-23 | 6 | [5 empty] | 6 | 0 | 0
2 | 11 | 1 | 3 | 電話（NTT） | ● |  |  |  | 李 明军 | 劉 嵩斌 |  | 2007-03-19 | 2007-03-23 | 6 | [5 empty] | 6 | 0 | 0
2 | 11 | 1 | 4 | 携帯電話（Docomo） | ● |  |  |  | 李 明军 | 劉 嵩斌 |  | 2007-03-19 | 2007-03-23 | 6 | [5 empty] | 6 | 0 | 0
2 | 11 | 2 |  | 受付業務結果照会 | ● |  |  |  | 李 明军 | 劉 嵩斌 |  | 2007-03-19 | 2007-03-23 | 8 | [5 empty] | 8 | 0 | 0
2 | 11 | 3 |  | 住所変更受付 | ● |  |  |  | 李 明军 | 劉 嵩斌 |  | 2007-03-19 | 2007-03-23 | 8 | [5 empty] | 8 | 0 | 0
2 | 12 |  |  | IB業務個別修正 | [14 empty] | 同上
2 | 12 | 1 |  | 資金移動時のソフトウェアパスワード | ● |  |  |  | 劉 嵩斌 | 李 明军 |  | 2007-03-14 | 2007-03-16 | 8 | [5 empty] | 8 | 0 | 0
2 | 12 | 2 |  | その他 | ● |  |  |  | 李 明军 | 李 明军 |  | 2007-03-19 | 2007-03-23 | 40 | [5 empty] | 40 | 0 | 0
2 | 13 |  |  | 行内業務修正 | ● |  |  |  | 郭 秀山 | 劉 嵩斌 |  | 2007-03-14 | 2007-03-23 | 40 |  |  |  |  | 同上 | 40 | 0 | 0
2 | 14 |  |  | PKG障害取込み | ● |  |  |  | 郭 秀山 | 劉 嵩斌 |  | 2007-03-14 | 2007-04-30 | 24 |  |  |  |  | 同上 | #REF! | #REF! | #REF!
纏め作業
3 | 1 |  |  | コード整合と修正 |  |  |  |  | 全員 |  |  | 2007-03-16 | 2007-04-02 | 80 |  |  |  |  | 同上 | 80 | 0 | 0
3 | 2 |  |  | コード・レビュー実施 |  |  |  |  | 全員 |  |  | 2007-03-26 | 2007-04-03 | 40 |  |  |  |  | レビュー結果 | 40 | 0 | 0
3 | 3 |  |  | コード・レビュー結果対応 |  |  |  |  | 全員 |  |  | 2007-04-03 | 2007-04-06 | 40 |  |  |  |  | レビュー対応結果 | 40 | 0 | 0
3 | 4 |  |  | UTレビュー |  |  |  |  | 全員 |  |  | 2007-04-03 | 2007-04-06 | 160 |  |  |  |  | レビュー結果 | 160 | 0 | 0
3 | 5 |  |  | UTレビュー結果対応 |  |  |  |  | 全員 |  |  | 2007-04-03 | 2007-04-06 | 80 |  |  |  |  | レビュー対応結果 | 80 | 0 | 0
内部設計
4 | 1 |  |  | 共通コンポーネント一覧/内部レビュー（必要な場合） | [7 empty] | 2007-04-16 | 2007-04-30 | 10 |  |  |  |  | コンポーネント一覧 | 10 | 0 | 0
4 | 2 |  |  | 業務コンポーネント一覧/内部レビュー（必要な場合） | [7 empty] | 2007-04-16 | 2007-04-30 | 10 |  |  |  |  | コンポーネント一覧 | 10 | 0 | 0
4 | 3 |  |  | SQL一覧/内部レビュー（必要な場合） | [7 empty] | 2007-04-16 | 2007-04-30 | 16 |  |  |  |  | SQL一覧 | 16 | 0 | 0
[13 empty] | SUM: | 2392
[14 empty] | 14.95 | MM
[20 empty] | PV | EV | AC | SV
[20 empty] | #REF! | #REF! | #REF! | #REF!
Formulas:
BCWS = IF([作成日]="","",IF([作成日]<=TODAY(),[更新者],IF([作成者]<=TODAY(),DAYS360([作成者],TODAY())/DAYS360([作成者],[作成日])*[更新者],0)))
BCWP = IF([作成日]="","",IF([更新日]<=TODAY(),[更新者]*IF([進捗]<>"",[進捗],0),0))
BCWP = IF(#REF!="","",IF([更新日]<=TODAY(),#REF!*IF([進捗]<>"",[進捗],0),0))
ACWP = IF([作成日]="","",IF([更新日]<=TODAY(),IF([実績工数(人時間）]<>"",[実績工数(人時間）],[更新者]*IF([進捗]<>"",[進捗],0)),0))
ACWP = IF(#REF!="","",IF([更新日]<=TODAY(),IF([実績工数(人時間）]<>"",[実績工数(人時間）],#REF!*IF([進捗]<>"",[進捗],0)),0))
江越さんに確認する必要がある。
江越さんに確認する必要がある。

## holiday
No | Date | holiday | Transfer Date
1 | 2019-06-07 | 端午节(CN)
2 | 2019-07-15 | 海洋节(JP)
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20